## BackLog
Epic | Task ID | Task Name | Description | Priority 0 - Low 5-Highest | Phase |  | Independent | Dependency Type | Asigneed | Status
Project Foundation | T002 | ARC Approval | Complete the ARC Approval from all stakeholders
Project Foundation | T003 | Tiering of Application | Need to get the BCP & IS Tiering
Project Foundation | T011 | ARN creation | Need to get IS & appropriate ARN team stakeholder
Project Foundation | T004 | Relevant IS Approval like VACA, cloud security &
Ingestion Pipeline | T006 | Document Collection & folder structures | Gather all RBI, WAF, IS, and Blueprint documents
Project Foundation | T007 | Environment Access Approval | Get Azure subscription access, RBAC roles, and network clearance
Project Foundation | T008 | Product backlog alignment | Finalize and approve detailed LLD document
Infrastructure Set-UP | T009 | Azure Environment Setup | Create RGs, VNets, Subnets, Key Vault, AI Search, Blob Storage
Infrastructure Set-UP | T010 | Security & Private Endpoint Configuration | Configure private endpoints, managed identities, NSGs
Submission & Pre-Processing Layer | T013 | Backend Setup (FastAPI) | Setup FastAPI backend with routes for LLM interaction
Submission & Pre-Processing Layer | T028 | Frontend UI Development | Build ReactJS/Streamlit UI for user submissions
Testing | T029 | Full E2E Testing | Perform UAT, performance, and regression testing
Closure | T033 | Knowledge Transfer & Closure | Prepare documentation, conduct KT, project closure sign-off
Submission & Pre-Processing Layer | T034 | API Schema Validation & Payload Contracts | Define JSON schema, validate submission payloads, and error handling patterns. |  |  | Sprint 0 | Yes | None | Added
Submission & Pre-Processing Layer | T035 | Mock Auth & RBAC Layer | Implement local mock of Entra ID validation; later switch to AAD integration. |  |  |  | Yes | None | Added
Submission & Pre-Processing Layer | T037 | Integrate API layer with Azure RBAC & Key Vault | Once Azure AD + Key Vault is provisioned, integrate managed identities and secrets. |  |  | Sprint 2 | No | Azure Access | Added
Orchestration & Workflow Engine | T038 | Autogen Controller Initialization | Define Orchestrator agent registry and config-driven routing JSON. |  |  | Sprint 0 | Yes | None | Added
Orchestration & Workflow Engine | T039 | DAG Manager & Dependency Graph Setup | Implement DAG logic inside Orchestrator (dependencies, preconditions). |  |  |  | Yes | None | Added
Orchestration & Workflow Engine | T040 | Timeout, Retry, DLQ Policy Framework | Define per-agent retry limits, backoff strategy, and DLQ store schema. |  |  |  | Yes | None | Added
Orchestration & Workflow Engine | T041 | Agent Context Passing & State Persistence (Cosmos Stub) | Implement in-memory mock for state store (e.g., SQLite / JSON). |  |  |  | Yes | None | Added
Orchestration & Workflow Engine | T042 | Integrate Orchestrator with Azure Services | Once Azure infra is live, swap mock state layer with actual services. |  |  |  | No | Azure Subscription | Added
Orchestration & Workflow Engine | T043 | Model Routing Intelligence (Azure Foundry Profiles) | Add rule engine to map task type → model profile (e.g., GPT-4o, Turbo, VLM). |  |  |  | Yes | None | Added
Orchestration & Workflow Engine | T044 | Coverage Check & Orchestrator Self-Healing | Implement logic to identify missing agent outputs and auto-trigger re-runs. |  |  |  | Yes | None | Added
Orchestration & Workflow Engine | T045 | Integrate Orchestrator with Azure OpenAI | Replace local mock models with Azure endpoints post-provisioning. |  |  |  | No | Azure AI Foundry | Added
Context Retrieval & RAG Layer | T047 | RAG Response Structuring & Normalization | Implement Top-K snippet formatter and metadata schema. |  |  |  | Yes | None | Added
Context Retrieval & RAG Layer | T048 | Redis Caching Layer Setup (Short TTL) | Implement cache for RAG queries with Redis or local memory cache. |  |  |  | Yes | None | Added
Context Retrieval & RAG Layer | T049 | Integrate Context Builder with Azure AI Search + Blob Storage | Replace local FAISS with Azure Cognitive Search index + Blob. |  |  |  | No | Azure Data Ingestion | Added
Context Retrieval & RAG Layer | T050 | Knowledge Graph Enrichment Hook | Add hooks in Context Builder for entity linking (phase 1 skeleton). |  |  |  | Yes | None | Added
Ingestion Pipeline | T026 | Document Upload & Indexing | Upload RBI/WAF/Blueprint docs to Blob Storage, generate embeddings
RAG Layer | T027 | Vector DB Validation | Validate search accuracy, ensure top-k retrieval correctness
Agent Framework & Worker Runtime | T051 | Agent Interface Standardization | Define input/output schema (JSON contract) across all agents. |  |  |  | Yes | None | Added
Agent Framework & Worker Runtime | T052 | Agent Test Harness (Local Runner) | CLI tool to invoke agents with mock inputs (for unit testing). |  |  |  | Yes | None | Added
Agent Framework & Worker Runtime | T053 | Agent Registry & Auto-Discovery | Registry for dynamically loading new agents into Orchestrator. |  |  |  | Yes | None | Added
Agent Framework & Worker Runtime | T054 | Integrate Agents with Azure Services | Bind worker subscriptions to queue topics. |  |  |  | No | Azure Service Bus | Added
Agent Framework & Worker Runtime | T055 | Clarifier Agent | Implement agent for low-confidence query clarification. |  |  |  | Yes | None | Added
Verification & Scoring Layer | T056 | CoVe Verifier Service | Build claim verification pipeline (LLM-based or deterministic). |  |  |  | Yes | None | Added
Verification & Scoring Layer | T057 | Scoring Engine Development | Compute per-agent + composite scores and confidence intervals. |  |  |  | Yes | None | Added
Verification & Scoring Layer | T058 | Push Scoring Metadata to Azure services | Sync scoring calibration into Knowledge Graph. |  |  |  | No | Azure Graph | Added
Report Generation & Notification | T059 | Report Composition Microservice | Generate JSON + PDF report with evidence snippets. |  |  |  | Yes | None | Added
Report Generation & Notification | T060 | Notification Webhook Framework | Stub backend callback endpoint to simulate final notification flow. |  |  |  | Yes | None | Added
Report Generation & Notification | T061 | Bind Blob URIs + Callback to Azure Notify | Final integration with Azure Blob & Service Bus. |  |  |  | No | Azure Storage | Added
Observability & Governance | T063 | Metric Definition and Log Schema Design | Define App Insights custom metrics schema. |  |  |  | Yes | None | Added
Observability & Governance | T064 | Link Logs to Azure Monitor and QRadar | Configure diagnostic settings once environment live. |  |  |  | No | Azure Monitor | Added
Integration & Stitching | T065 | Integrate FastAPI with Azure AD & Key Vault | Secure APIs with RBAC + managed identities. |  |  |  | No | Azure Access | Added
Integration & Stitching | T066 | Integrate Orchestrator with Azure Service Bus + CosmosDB | Replace local mocks with Azure messaging & persistence. |  |  |  | No | Azure Subscription | Added
Integration & Stitching | T068 | Integrate Agents with Azure OpenAI & AI Foundry | Enable real LLM inference. |  |  |  | No | Azure OpenAI | Added
Integration & Stitching | T069 | Integrate Observability stack (Logs → App Insights → QRadar) | End-to-end traceability. |  |  |  | No | Azure Monitoring | Added
Integration & Stitching | T070 | Platform-Level Integration Validation | E2E testing across all layers after infra readiness. |  |  |  | No | Cross-Module | Added
Prompt Building & Optimization | T071 | Prompt Template Library Setup | Design YAML/JSON templates per agent type. |  |  |  | Yes | None | Added
Prompt Building & Optimization | T072 | Prompt Injection Framework | Inject context (RAG + constraints) into templates. |  |  |  | Yes | None | Added
Prompt Building & Optimization | T073 | Prompt Validation Utility | Validate prompt format, tokens, schema before LLM call. |  |  |  | Yes | None | Added
Prompt Building & Optimization | T074 | LLM Call Manager for Prompt Execution | Wrapper for all model calls (OpenAI/Azure Foundry). |  |  |  | Yes | None | Added
Prompt Building & Optimization | T075 | Prompt Feedback Capture & Logging | Log prompt input/output and quality metrics. |  |  |  | Yes | None | Added
Prompt Building & Optimization | T076 | Instruction Optimization & Guardrails | Add rules for context boundary, tone, determinism. |  |  |  | Yes | None | Added
Prompt Building & Optimization | T077 | Adaptive Feedback Loop (Prompt Scoring) | Feedback scoring mechanism for iterative improvement. |  |  |  | Yes | None | Added
Prompt Building & Optimization | T078 | Prompt Evaluation Dataset Creation | Curate success/failure prompt dataset for scoring. |  |  |  | Yes | None | Added
Prompt Building & Optimization | T079 | Connect Prompt Layer to Azure AI Foundry | Integrate prompt executor with Azure-hosted endpoints. |  |  |  | No | Azure AI Foundry | Added
Prompt Building & Optimization | T080 | Enable Prompt Performance Telemetry in Azure Monitor | Capture latency, tokens, and errors into App Insights. |  |  |  | No | Azure Monitoring | Added
Agent Framework & Worker Runtime | T081 | Agent Controller & Orchestration Logic | Develop controller logic to manage agent parallel/cascade execution flow. |  |  |  | Yes | None | Added
Agent Framework & Worker Runtime | T082 | Template Agent Development | Build base JSON/metadata generation agent. |  |  |  | Yes | None | Original
Agent Framework & Worker Runtime | T083 | Demographics Agent Development | Capture org/app metadata. |  |  |  | Yes | None | Original
Agent Framework & Worker Runtime | T084 | Sizing Agent Development | Validate compute/storage sizing. |  |  |  | Yes | None | Original
Agent Framework & Worker Runtime | T085 | API Validation Agent Development | Validate APIs vs governance standards. |  |  |  | Yes | None | Original
Agent Framework & Worker Runtime | T086 | Tech Stack Agent Development | Validate frameworks, middleware, runtime usage. |  |  |  | Yes | None | Original
Agent Framework & Worker Runtime | T087 | Port & Connectivity Agent Development | Validate allowed ports and network topology. |  |  |  | Yes | None | Original
Agent Framework & Worker Runtime | T088 | IS Policy Agent Development | Validate encryption, IAM, and DLP policies. |  |  |  | Yes | None | Original
Agent Framework & Worker Runtime | T089 | Tiering Agent Development | Validate DR/HA, backup configuration. |  |  |  | Yes | None | Original
Agent Framework & Worker Runtime | T090 | Architecture Agent Development | Perform holistic EA validation against standards. |  |  |  | Yes | None | Original
Agent Framework & Worker Runtime | T091 | Formatting Agent Development | Ensure document consistency and audit readiness. |  |  |  | Yes | None | Original
Agent Framework & Worker Runtime | T092 | Scoring Agent Development | Compute overall and component-level scores. |  |  |  | Yes | None | Added
Agent Framework & Worker Runtime | T093 | CoVe Verifier Agent Development | Validate factual accuracy via chain-of-verification. |  |  |  | Yes | None | Added
Agent Framework & Worker Runtime | T094 | Clarifier Agent Development | Ask clarifying questions for missing or low-confidence outputs. |  |  |  | Yes | None | Added
Submission & Pre-Processing Layer | T095 | Two-step Upload Flow & Chunked Upload Support | Implement /upload -> file_id then /review using file_id; support chunked uploads for large files and resume. |  |  |  | Yes | None | Added
Submission & Pre-Processing Layer | T096 | File Type Whitelist & MIME Validation | Strict file type and MIME checks; reject unsupported types with clear errors. |  |  |  | Yes | None | Added
Submission & Pre-Processing Layer | T098 | Image OCR & VLM Preprocessor | Extract text from diagrams/images via OCR/VLM and store for indexing. |  |  |  | Yes | None | Added
Submission & Pre-Processing Layer | T099 | File Size & Page Limits Enforcement | Enforce limits (single file, pages) and async ingestion path for larger files. |  |  |  | Yes | None | Added
Submission & Pre-Processing Layer | T100 | Metadata Enforcement & Enrichment | Require submitter_id, business_unit, doc_type, intended_review_scope; enrich with derived metadata. |  |  |  | Yes | None | Added
Context Retrieval & RAG Layer | T101 | Document Ingestion Pipeline (embed + index) | ETL pipeline to convert docs -> embeddings -> index in Azure AI Search + Blob storage lifecycle. |  |  |  | No | Azure Blob + AI Search | Added
Context Retrieval & RAG Layer | T102 | Embedding Generation Service | Service to call embeddings model, manage batch, retry & store vectors. |  |  |  | No | Azure OpenAI / Foundry | Added
Context Retrieval & RAG Layer | T103 | Index Versioning & Reindex Strategy | Versioned indexing, reindex triggers on policy updates and document updates. |  |  |  | Yes | None | Added
Context Retrieval & RAG Layer | T104 | Embedding Refresh & Re-training Hook | Hook to refresh embeddings periodically or after feedback loop - ties to continuous learning. |  |  |  | No | Data Ingestion | Added
Security & Governance | T105 | Key Vault Secrets Rotation & Management | Automate rotation of keys, credentials and integrate with Key Vault access policies. |  |  |  | No | Azure Key Vault | Added
Security & Governance | T106 | Network Security: NSG & Private Endpoint Tests | Automated validation tests for private endpoint connectivity and NSG rules. |  |  |  | Yes | None | Added
Security & Governance | T107 | RBAC Provisioning Automation (ARM/Terraform) | IaC templates for role assignments, managed identities and resource provisioning. |  |  |  | No | Azure Subscription | Added
Security & Governance | T108 | Data Encryption & Data-at-Rest Policy Validation | Ensure AES-256 at rest, TLS for transit; compliance checks. |  |  |  | Yes | None | Added
Orchestration & Workflow Engine | T109 | Agent Controller: Parallel vs Cascade Execution Modes | Explicit task to implement parallel and cascade execution modes, with config flags per workflow. |  |  |  | Yes | None | Added
Agent Framework & Worker Runtime | T110 | Worker Concurrency & Autoscaling Strategy | Implement worker pooling, concurrency limits, and autoscaling (AKS/HPA). |  |  |  | No | Kubernetes/AKS | Added
Agent Framework & Worker Runtime | T111 | Agent-Level Monitoring (per-agent traces & cost metrics) | Emit per-agent metrics: latency, token usage, cost estimates, success/failure. |  |  |  | Yes | None | Added
Agent Framework & Worker Runtime | T112 | Diagram Parsing (VLM) Agent Implementation | Specific agent to parse diagrams with VLM and extract entities/relations. |  |  |  | Yes | None | Added
Prompt Building & Optimization | T113 | Prompt Token Budgeting & Truncation Rules | Implement token budget logic, truncation and attachment_refs strategy for long contexts. |  |  |  | Yes | None | Added
Prompt Building & Optimization | T114 | Model Parameter Profiles (temp, max_tokens, stop) | Define and store model param profiles per template and agent. |  |  |  | Yes | None | Added
Prompt Building & Optimization | T115 | Prompt A/B Testing Harness | Support A/B experiments to compare prompt templates and model outputs. |  |  |  | Yes | None | Added
Verification & Scoring Layer | T116 | Grounding Confidence Thresholds & Action Rules | Define thresholds that drive clarification, human review, or auto-accept. |  |  |  | Yes | None | Added
Verification & Scoring Layer | T117 | Evidence Linkage & Reference Resolver | Service to map findings to exact document locations and create evidence bundles. |  |  |  | Yes | None | Added
Observability & Governance | T118 | Alerting & SLO Definitions | Define SLOs and configure alerts for failures, timeouts, and high error rates. |  |  |  | Yes | None | Added
Observability & Governance | T119 | Security & Vulnerability Scanning (CI Pipeline) | Integrate SAST/DAST, dependency scanning into CI/CD pipelines. |  |  |  | Yes | None | Added
DevOps & Deployment | T120 | CI/CD Pipelines (Build/Test/Deploy) | Pipelines for FastAPI, Agents, Orchestrator, and infra IaC; include Canary/Blue-Green options. |  |  |  | No | Azure DevOps/GitHub Actions | Added
DevOps & Deployment | T121 | Container Registry & Image Hardening | Store images in ACR, implement image scanning and signing. |  |  |  | No | Azure Container Registry | Added
Human-in-the-loop | T122 | Reviewer Triage & Dashboard Features | UI features for human reviewers: prioritize queue, annotate, accept/reject, feedback capture. |  |  |  | Yes | None | Added
Human-in-the-loop | T123 | Feedback Integration to Retrain Embeddings | Mechanism to feed reviewer labels back into embedding refresh or prompt tuning. |  |  |  | No | Feedback Data + Training infra | Added
Reporting & Audit | T124 | Long-term Retention & Archival Policy Implementation | Automate retention policy for reports and audit logs (7-year compliance). |  |  |  | No | Blob Lifecycle | Added
Reporting & Audit | T125 | Immutable Audit Log Verification & Tamper-evidence | Ensure the audit store is append-only and verifiable; implement monitoring to detect tampering. |  |  |  | No | CosmosDB / AuditStore | Added
Platform Resilience | T126 | Load & Stress Testing (Agents & Orchestrator) | Perform load tests and tune concurrency/throughput. |  |  |  | Yes | None | Added
Platform Resilience | T127 | Chaos & Failure Injection Tests | Introduce fault injection to ensure graceful degradation and DLQ behavior. |  |  |  | Yes | None | Added
Cost Management | T128 | Model Usage Cost Controls & Quotas | Implement token/cost caps per request and per tenant to avoid runaway costs. |  |  |  | Yes | None | Added

## Sprint 0( 27-10 to 7-11)
SPRINT | TASK ID | TASK | Sub Tasks | Asignee
Sprint 0 | T004 | Relevant IS Approval like VACA, cloud security | Follow-up with Deepak Kotian for process for Azure access request | Rahul / Sneha
Sprint 0 | T011 | ARN creation | Process & Initiation | Rahul
Sprint 0 | T006 | Collection of all documents Document Structuring and Follow-up | 1. Sharepoint folder structure 2. Document Matrix - Doc Name, Document purpose , Doc content and aligned agent 3. Follow-up for sourcing the data | Raj / Sneha
Sprint 0 | T038 | Autogen Controller Initialization | Define Orchestrator agent registry and config-driven routing JSON. Detail-out metadata required by the controller from the Fast API | Mohan
Sprint 0 | T034 | API Schema Validation & Payload Contracts | Define JSON schema, validation of payloads, and error handling patterns. | Priyal
Sprint 0 | T098 | Image OCR & VLM Preprocessor | Strategy to Extract text from diagrams/images via OCR/VLM and store for indexing.Image source Image classification ( network , infra, workflow, datamodel etc.) Service ( azure ) used for image reading | Priyal
Sprint 0 | T004 | Get Azure subscription access, RBAC roles, and network clearance |  | Raj / Sneha
Sprint Demo / Review
1. Autogen orchestrator --> Controller framework ( inputs ) 2. Documentation (un)/available, categorised and verified matrix of documents aligned to the agents 3. JSON Standardization -metadata finalisation -impact and usage of the metada - garauntee coverage and extensibility 4 . Image Handling Strategy

## Sprint 1(10-11 to 21-11)
SPRINT | TASK ID | TASK | Sub Tasks | Asignee
Sprint 1 | T009 | Azure Infra set-up | Create RGs, VNets, Subnets, Key Vault, AI Search, Blob Storage as per YBL policies Configure private endpoints, managed identities, NSGs | Priyal / Raj
Sprint 1 | T013 | Setup FastAPI backend |  | Mohan
| T028 | Frontend UI Development | Build ReactJS/Streamlit UI for user submissions | Mohan
Sprint 1 | T026 | Document Upload & Indexing | Upload RBI/WAF/Blueprint docs to Blob Storage, generate embeddings | Raj / Priyal
Sprint 1 | T027 | Vector DB Validation | Validate search accuracy, ensure top-k retrieval correctness | Kishore
Sprint 1 | T042 | Integrate Orchestrator with Azure Services | Once Azure infra is live, swap mock state layer with actual services. | Mohan
| T081 | Agent Controller & Orchestration Logic | Develop controller logic to manage agent parallel/cascade execution flow. | Mohan
Sprint Demo / Review
1. Autogen orchestrator --> Dry run with mock agents 2. Data Structure and Embedding 3. Front end integrated with FastAPI